## Sheet1
Tasks | Weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Initiating
Assign project manager
Develop project charter
Meet with stakeholders
Planning
Create scope plan
Create WBS and schedule
Create procurement plan
Create Project Mgmt. Plan
Executing
Develop network configuration
Remove all HW
Order SW and HW
Install new SW on servers
Install new HW and SW on client’s machines
Test new billing system
Controlling
Status reports
Update plans
Closing
Lessons learned
Prepare final report

## Sheet3
Tasks | Weeks (5 business day per week)
| 1 31/07 - 4/07 | 2 7/08 - 11/08 | 3 14/08 - 18/08 | 4 21/08 - 25/08 | 5 28/08 - 1/09 | 6 4/09 - 8/09 | 7 11/09 - 15/09 | 8 18/09 - 22/09 | 9 25/09 - 29/09
Initiating
Assign project manager
Develop project charter
Meet with stakeholders
Planning
Create scope plan
Create WBS and schedule
Create procurement plan
Create Project Management Plan
Executing
Develop network configuration
Remove all hardware (HW)
Order software (SW) and HW
Install new software on servers
Install new HW and SW on client’s machines
Test new billing system
Controlling
Status reports
Update plans
Closing
Lessons learned
Prepare final report
Note:
The project charter can provide information about internal and external parties involved in and affected by the project, such as project sponsor(s), customers, team members, groups and departments participating in the project, and other people or organizations affected by the project.
Creating Work Breakdown Structure (WBS) is the process of subdividing project deliverables and project work into smaller, more manageable components.
Developing Schedule is the process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule.
Developing Project Management Plan is the process of documenting the actions necessary to define, prepare, integrate, and coordinate all subsidiary plans.